## Risks
Analysis of National Learning Assessment Systems (ANLAS)
Risks and mitigation strategies
Risk number # | Risk cause | Risk effect | Likelihood (almost certain, likely, possible, unlikely or rare) | Consequences (negligible, minor, moderate, major, or crucial) | Risk ranking (low, moderate, high, or very high) | Mitigation strategies | Owner of mitigation strategy
Example 1 | Particular documents needed to complete ANLAS analytical tables are not publicly available. | Delays in accessing documents, due to formal permissions needing to be sought; information is not available to team resulting in a gap in the information provided in the ANLAS analytical tables. | Likely | Crucial | Very High | 1. Identify documents needed for the analysis and document these in the ANLAS document mapping table and undertake permissions process as early as possible. 2. Identify other possible sources of information if document is unavailable (for example, stakeholder consultations). 3. Document any limitations in data collection in the report. | 1. National team 2. National team 3. National team
Example 2 | Delays in the work due to competing work demands for the national team. | Delays in the project schedule and meeting deliverable deadlines. National team unable to complete ANLAS tasks in a timely manner due to commitments to other projects. | Almost certain | Moderate | High | 1. Increase the number of national team members. 2. Delegate ANLAS tasks amongst all national team members. | 1. National team 2. National team
Example 3 | Relevant stakeholders may not be available during data collection and consultation due to other work demands and/or due to local events (for example presidential elections, teachers' strike). | Delay in data collection timeline. Information may not be available for the purpose. National team spends a lot of time scheduling stakeholder consultations and following up to secure availability. | Possible | Minor | Moderate | 1. Identify and schedule other possible sources of information if particular stakeholders are unavailable. 2. Provide stakeholders with several appointment dates and times. 3. Document any limitations in data collection in the country report. | 1. National team 2. National team 3. National team

## Risk framework
Likelihood | Consequences
| Negligible | Minor | Moderate | Major | Crucial
Almost certain | Moderate | Moderate | High | Very High | Very High
Likely | Moderate | Moderate | High | High | Very High
Possible | Low | Moderate | High | High | High
Unlikely | Low | Low | Moderate | Moderate | High
Rare | Low | Low | Moderate | Moderate | High

## Do not edit
Almost certain
Likely
Possible
Unlikely
Rare
Negligible
Minor
Moderate
Major
Crucial